Action Plan

Executive Summary

This action plan outlines the steps to be taken by the Master Data Management (MDM) department over the next month. The plan focuses on four key objectives:

- Understanding the business context and expectations regarding data management.

- Assessing the current MDM processes and systems.

- Identifying and Prioritizing MDM Projects.

- Building Awareness and Obtaining Buy-in.

| Tasks | Assigned to | Due date | Name of Coach |
| --- | --- | --- | --- |
| 1. Understanding the Business and Expectations: - Reviewing the organization's structure and operations to understand data dependencies. - Analyzing how MDM can support strategic goals and address critical data-related challenges. | Bulte Belay Dinkensh Getachew Temare Asefa Dawit Shibabaw | 19/02/2024 | Betelhem B |
| 2. Assess Current MDM Processes: - Evaluating existing MDM processes, tools, and technologies. - Reviewing data governance policies, frameworks and compliance requirements. - Assessing data quality and consistency across systems and databases. - Perform data quality assessments. | Bulte Belay Dinkensh Getachew Temare Asefa Dawit Shibabaw | 02/03/2024 | Mikias T |
| 3. Identifying and Prioritizing MDM Projects: - Analyze findings from the assessment of existing MDM processes and data management practices. - Identify potential MDM projects that address critical data quality issues, compliance requirements, or strategic business objectives. - Prioritize MDM projects based on their anticipated impact, urgency, and resource availability. . | Bulte Belay Dinkensh Getachew Temare Asefa Dawit Shibabaw | 16/03/2024 | Yonatan S |
| 4. Building Awareness and Obtaining Buy-in: - Develop a communication plan to raise awareness of MDM initiatives and their importance to the organization. - Provide training and education sessions to ensure understanding of MDM principles, benefits, and impact on business operations. | Bulte Belay Dinkensh Getachew Temare Asefa Dawit Shibabaw | 30/03/2024 | Freweyni G and Addisu K |